## Sheet1
Task | Start | Finish | Completion %
Project 1 | 2021-03-05 | 2021-12-31 | 100
Complete algorithm to generate simulated AMSR-E & target arrays from LLC4320 | 2021-03-05 | 2021-03-19 | 100
Apply algorithm to the hourly LLC datasets | 2021-03-22 | 2021-03-29 | 100
Gain familiarity with Brahim's model | 2021-03-19 | 2021-03-26 | 100
Zoom with Brahim | 2021-03-29 | 2021-04-02 | 100
Train NN with subset of LLC dataset | 2021-03-30 | 2021-04-20 | 100
Feed real AMSRE into NN | 2021-04-21 | 2021-04-28 | 100
Identify metric to evaluate the performance of NN with real data | 2021-04-23 | 2021-05-07 | 100
Write first paper | 2021-03-05 | 2021-10-29 | 100
Writing intro to SST paper and framework | 2021-03-05 | 2021-05-21 | 100
First draft of thesis proposal | 2021-05-24 | 2021-09-06 | 100
Submit manuscript for paper 1 | 2021-09-07 | 2021-10-29 | 100
Compare NN to David Long's work | 2021-05-21 | 2021-05-21 | 100
Investigate Japanese AMSR3 SST retrieval algorithm |  | 2021-05-21 | 100
Generate enhanced AMSRE 10x10 for entire dataset | 2021-05-24 | 2021-11-26 | 100
Enhance AMSR2 and test performance | 2021-11-29 | 2021-12-31 | 100
Paper 2 | 2022-01-01 | 2022-12-31 | 100
Port approach to other ocean products | 2022-01-03 | 2022-12-31 | 100
Paper 3 | 2023-01-02 | 2023-12-31 | 100
Focus on terrestrial & cryospheric products | 2023-01-02 | 2023-12-31 | 100