## Sheet1
Task | Start | Finish | Completion %
Task 1: Individual Investigation of Possible Project Topics | 2024-09-18 | 2024-09-20 | 100
Task 2: Topic Chosen by Team | 2024-09-20 | 2024-09-24 | 100
Task 3: Identify stakeholders and issues. | 2024-09-22 | 2024-09-24 | 100
Task 4: Agree upon the stakeholder(s) and issue(s) each team member will investigate further. | 2024-09-23 | 2024-09-30 | 100
Task 5: Begin to make slides. | 2024-09-23 | 2024-10-21 | 100
Task 6: Further investigation by individual team members, alternative courses of action and the effects from perspective of stakeholder | 2024-10-10 | 2024-10-24 | 100
Task 7: Correlate perspectives and make a decision. | 2024-10-22 | 2024-10-24 | 100
Task 8: As a team, use a weighted benefit analysis to show how you made your decision. | 2024-10-18 | 2024-10-25 | 0
Task 9: Slides compiled for team presentation. | 2024-10-21 | 2024-10-30 | 0
Task 10: Presentation during the lab period. | 2024-10-29 | 2024-10-30 | 0